## Sheet1
. Calculating Project Difficulty
Project Name: | Project Name |  |  |  |  | Score | Wt. Use | Value | Set
Project Type: | Project Type | [7 empty] | Weighting
Size | Much smaller | Smaller | Similar | Larger | Much larger
[7 empty] | 1.0385 |  | 1 |  | 1
Technical Difficulty (complication) | Much less | Less | Similar | Greater | Much Greater | [5 empty] | 2
[7 empty] | 1.0385 |  | 1 |  | 3
What is to be delivered | Fully defined | Partially defined | Objectives defined | Objectives outlined | Unclear | [5 empty] | 4
[7 empty] | 2.0769 |  | 2 |  | 5
How the product is to be created | Fully understood | Partially understood | General approach | Conceptual framework | Unclear
[7 empty] | 3.1154 |  | 3
Key Stakeholder Support | Generally committed | Generally supportive | Ambivalent | Some opposition | Generally antagonistic
[7 empty] | 1.0385 |  | 1
Team structure | Very simple | Simpler than normal | Normal for type | More complicated | Complicated arrangements
[7 empty] | 4.1538 |  | 4
Project Risk Profile | Low | Normal | High | Very High | Extreme
[7 empty] | 4.1538 |  | 4
Complexity of Work | Simple | Normal | Normal + Political | Complex | Highly Complex
[7 empty] | 5.1923 |  | 5
Complexity of Developing Product | Done many times before | Done once or twice before | Components done before in different context | New technical systems required | New theory to develop and implement
[7 empty] | 5.1923 |  | 5
Factor
Calculated Relative Difficulty: |  | To be assessed | [5 empty] | 0 | 26 | 1.0385
Instructions for use
1. For the type of project being assessed, determine the characteristics of a 'normal' project for your organization.
2. Review and adjust the relative weighting against each category of difficulty in the range 1 to 5 1 is relatively less important, 5 is of significant importance to the assessment.
3. For each category of difficulty, place an 'X' under the term that best describes the project being assessed compared to the normal project for this type.
4. When complete, the spreadsheet calculates the degree of difficulty from 'Simple' to 'Extreme', based on the assessment and weightings applied. Both can be adjusted.
5. For more on classifications see: | https://mosaicprojects.com.au/WhitePapers/WP1072_Project_Categorisation.pdf
Developed by Mosaic Project Services Pty Ltd: |  | https://mosaicprojects.com.au/PMKI-ORG-035.php
Mosaic has a range of practical templates, tools, and books available to buy from our shop: |  |  |  | https://mosaicprojects.com.au/shop.php
The Mosaic PMKI Library has a large selection of papers and articles available free of cost: |  |  |  | https://mosaicprojects.com.au/PMKI.php