## Data
Easy EVM Workbook
Sample Rail Bridge EVM | [8 empty] | Update Date: | 2022-02-21 |  |  |  |  | ETC: | 10867781.4371 | EAC: | 15059281.4371 | VAC: | -59281.4371
WP # | WP Description | Baseline Values |  |  | Actual This Update | [5 empty] | Baseline Duration | Baseline to Date | Planned Value | Actual Duration | Earned Value | SV | SPI | CV | CPI | Errors
|  | Start | End | $ Budget | Start | End | Account Costs | Acrual Costs | AC | %*
Project totals = |  | 2021-11-15 | 2022-09-15 | 15000000 | 2021-11-15 | - | 3669000 | 522500 | 4191500 | - | 304 | 98 | 4010642.3329 | 98 | 4175000 | 164357.6671 | 1.041 | -16500 | 0.99606
1.1 | Project management and overheads | 2021-11-15 | 2022-09-15 | 850000 | 2021-11-15 |  | 266000 | 8000 | 274000 | 32% | 304 | 98 | 274013.1579 | 98 | 272000 | -2013.1579 | 0.99265 | -2000 | 0.9927
1.2 | Site management and services | 2022-01-02 | 2022-09-15 | 600000 | 2022-01-10 |  | 82000 | 9500 | 91500 | 15% | 256 | 50 | 117187.5 | 42 | 90000 | -27187.5 | 0.768 | -1500 | 0.98361
2 | Design & Approvals | 2021-11-15 | 2022-01-31 | 1550000 | 2021-11-15 | 2022-01-20 | 1558000 |  | 1558000 | 100% | 77 | 77 | 1550000 | 66 | 1550000 | 0 | 1 | -8000 | 0.99487
3.1 | Site set up | 2022-01-02 | 2022-01-31 | 300000 | 2022-01-15 | 2022-02-10 | 255000 | 60000 | 315000 | 100% | 29 | 29 | 300000 | 26 | 300000 | 0 | 1 | -15000 | 0.95238
3.2 | Earth works | 2022-01-20 | 2022-03-20 | 1500000 | 2022-01-25 |  | 900000 | 210000 | 1110000 | 75% | 59 | 32 | 813559.322 | 27 | 1125000 | 311440.678 | 1.3828 | 15000 | 1.0135
3.3 | Manfr. & Install PC Bridge Deck | 2022-01-02 | 2022-07-25 | 3900000 | 2021-12-20 |  | 600000 | 190000 | 790000 | 20% | 204 | 50 | 955882.3529 | 63 | 780000 | -175882.3529 | 0.816 | -10000 | 0.98734
3.4 | Concrete piers & walls | 2022-03-01 | 2022-05-30 | 2900000 | 2022-02-15 |  | 8000 | 45000 | 53000 | 2% | 90 |  |  | 6 | 58000 | 58000 | N/A | 5000 | 1.0943
3.5 | Embankment works | 2022-05-30 | 2022-07-10 | 1200000 | [6 empty] | 41
3.6 | Track works | 2022-07-26 | 2022-08-30 | 1700000 | [6 empty] | 35
3.7 | Clear Site & Make Good | 2022-08-30 | 2022-09-15 | 500000 | [6 empty] | 16
Formulas:
Actual This Update = IF(MIN(G9:G44)<[Baseline Values],MIN(G9:G44),[Baseline Values])

## Instructions
|  | Easy EVM Workbook | This worksheet should be used in conjunction with Easy EVM. It is appropriate for smaller ICT (<$2 million) and Engineering projects (<$20 million) with up to 35 work packages. Larger projects require the use of commercial EVM software.
User Instructions
1 | The worksheet is designed to process the data for a single update. After each update is complete, save a copy of the spreadsheet ready for the next update and then edit / add the new information.
2 | The worksheet is protected, data can only be entered in the cells shaded light green.
3 | Work package numbers and descriptions are free-form and can be edited to suit the needs of the project. Once created, these should not change.
4 | It is recommended a schedule be set up for the project with the following characteristics: 1. The schedule contains a summary activity for each work package with detail tasks below 2. The summary activity be set up to roll up 'physical percent complete' from the activities 3. Dates and percent complete are transcribed from the schedule
5 | Baseline start and end dates are obtained from the schedule and transcribed into the relevant fields. Once entered, these should not be changed.
6 | Baseline budget values are obtained from the project budget. Once entered these values should not be changed. The total budget (BAC) is summed at the top of the table for verification.
7 | Any change to the baseline values should be approved and fully documented. See Easy EVM, Section 4.2.4.
8 | The update date is entered at the top of the table, this should be the same date as used to update the schedule.
9 | The actual start date for the work package is obtained from the schedule. Once entered, this should not be changed.
10 | The worksheet assumes progress within the work package is uniform, therefore once started, an actual cost value and a percent complete value must be entered. $1 and 1% are acceptable.
11 | The actual finish date for the work package is obtained from the schedule. Once entered, this should not be changed.
12 | The Actual Cost (AC) comprises two values, the actual costs for the work package recorded in the project accounting system, plus an accrual value to cover the cost of work performed, but not yet recorded in the project accounts, the accrual will typically be an estimate revised at each update.
13 | The physical percent (%) complete is either derived from the schedule (preferred) or estimated.
14 | The calculated variance for each work package in progress should be reviewed and actioned. See Easy EVM Section 4.4.
15 | Trend information is valuable, reviewing changes in a work package over several updates (saved worksheets) will indicate if the project situation is improving or deteriorating.
Calculated Fields
| AC = Actual cost to date, the sum of the 'account costs' and 'accrual costs'. |  | For more on Easy EVM see: https://mosaicprojects.com.au/shop-easy-evm.php
Planned Value (PV) = The amount of the baseline budget planned to have been accomplished by the update date. PV is $0 if the work package has not been planned to start. PV is calculated based on elapsed calendar days.
| Earned Value = The value of work performed, based on the physical percent complete. |  | Free EVM resources see: https://mosaicprojects.com.au/PMKI-SCH-040.php
SV = Schedule Variance, the difference between the earned value and the planned value.
SPI = Schedule Performance Index, the ratio of earned value divided by planned value.
CV = Cost Variance, the difference between the earned value and the actual cost (AC).
CPI = Cost Performance Index, the ratio of earned value divided by actual cost (AC).
ETC = Estimate to complete, EAC - AC.
EAC = Estimate at completion, (BAC - EV)/CPI + AC.
VAC = Variance at Completion, budget at completion - EAC.
Errors = Data inconsistencies.