## RMP
Project Title | [5 empty] | Note: Status, In Schedule and In Cost Plan refer to the specific risk treatment activities in this worksheet, not the primary project works. |  |  |  | Worksheet Design: © 2009 Mosaic Project Services Pty Ltd www.mosaicprojects.com.au
ID | Classification | Description of Risk (Paste RMP Export data into these fields) | Grade | Proposed Actions | Suggestions | Agreed Actions (One Action Per Line) | Responsible Owner | Status | In Schd'l | In Cost Plan | Notes
A200 | Time | Storms: If a heavy thunderstorm caused by summer heat occurs, it may cause flooding and consequential cleanup. The impact of this threat is: delays and associated costs. | B | Mitigate | Enhance drainage |  | The project manager | Open |  |  | Responsible for decisions based on outcomes from actions
[6 empty] | Assess likely frequency and intensity of storms in area based on recorded data | Administrator | In Progress | N/A | N/A | No cost | Open | Yes
[6 empty] | Design temporary drainage channels | Engineer | On Hold | No | No | Awaiting weather data | In Progress | N/A
[6 empty] | Let contract to install channels | Administrator | On Hold | N/A | No | Ditto | On Hold | No
[6 empty] | Undertake the work | TBA | On Hold | No | No | Ditto | Closed
A002 | Quality / Scope | Skills: If a shortage of skilled workers caused by industry demand occurs, it may cause an increase in test failures. The impact of this threat is: delays, rework and increased costs. | A | Transfer | Contract development to a capable organisation | Include in selection criteria for contractors | Contract Admin | In Progress | N/A | N/A | Unlikely to have time or cost impact on project but should be a key assessment criteria.
A003 | Cost / Value | Exchange Rates: If a improvement in the exchange rates caused by the value of the AU$ occurs, it may cause off-shored work will become cheaper. The impact of this opportunity is: improving profitability. | D | Enhance | Monitor the exchange rate and include in decisions on contracts | Request monthly trend forecasts from finance | Administrator | Closed | N/A | N/A | Reports requested
[6 empty] | Review trends and include recommendation in monthly meeting agenda | Administrator | In Progress | N/A | N/A | Further action will depend on the actual information provided
Not available in Sample Version

## Instructions
Mosaic Project Services Pty Ltd
13 Martin Street
© Practical PMP Pty Ltd, 2010 |  |  |  |  | South Melbourne, VIC 3205, Australia
Use of Spreadsheet |  |  |  |  | www.mosaicprojects.com.au
Risk Management |  |  |  |  | Support: | help@mosaicprojects.com.au
For each identified risk requiring action, a specific risk management plan should be developed. |  |  |  |  | Sales: | www.mosaicprojects.com.au
The RMP is built in this spreadsheet.
Copy the risks into the risk Management Plan (RMP):
Risks are copied across one at a time, starting with the most urgent (ie, requiring immediate attention)
Copy the risk from the 'green' area of the Risk Register and pase into the corresponding area in this spreadsheet.
Then develop the risk management plan (treatments) for the risk. This may need several lines of information.
Once the RMP is complete for the first risk, copy the next risk across.
Developing the Risk Treatment
Any plan to exploite, avoid, transfer, share, mitigate of enhance the effect of a risk requires specific actions.
This spreadsheet defines those actions and allocates a respnsible manager.
Developing the action list
For each risk, define the specific actions required to manage the risk effectively, these need to be SMART
SMART = Specific, Measurable, Actionable, the Responsibility of a person and Time framed
Define the action Responsible Owner, the person responsible for implementing the action
You may have an overall 'risk owner' and different people allocated for specific actions
Set the current status for the risk (this should be updated regualrly)
|  |  | Open | Not yet actioned
|  |  | In Progress | Action being implemented
|  |  | On Hold | Usually awaiting the outcome of a previous action but may be any enforced delay
|  |  | Closed | Action completed or no longer required
Included in the Schedule and/or the Cost Plan
Every action is likely to have time and or cost consequences. These need to be incorporated into the project plans.
Set the current status for the risk (this should be updated regualrly)
|  |  | Yes | Information is included in the schedule and/or cost plan
|  |  | N/A | There is no effect on either the schedule or the cost plan
|  |  | No | Information has still to be integrated into the schedule and/or cost plan
Notes
Include any notes needed for future references
Review the Risk Treatment
The RMP should be reviewed regualry. This is not the same as a 'Risk Review' where the risk register is updated.
RMP reviews are to ensure the planned actions are being accomplished in a timely way, it is part of the routine management of the work.
Risk Reviews take place at key milestones and/or scheduled intervals and acssess the overall risk profile of the project.