## Risk Register
Your Project Name | [14 empty] | Worksheet Design: © 2010 Mosaic Project Services Pty Ltd www.mosaicprojects.com.au |  | RMP Export - Copy each risk in turn to export to RMP Template
ID | Classification | Full Risk Statement (the description builds as you complete the spreadsheet) | Short Name | Description of Risk If a | Cause of Risk caused by | Consequences of Risk occurs, it may cause | Opportunity Threat | Impact on Project | Probability | Impact |  |  |  | Grade | Proposed Response | Suggested Actions / Options | ID | Classification | Full Description Short name + Cause + Consequence and Impact | Grade | Response | Suggestions
A001 | Time | Storms: If a heavy thunderstorm caused by summer heat occurs, it may cause floding and consequential cleanup. The impact of this threat is: delays and associated costs. | Storms | heavy thunderstorm | summer heat | floding and consequential cleanup | threat | delays and associated costs | M | H | 0.5 | 0.75 | 1.25 | B | Mitigate | Enhance drainage | A001 | Time | Storms: If a heavy thunderstorm caused by summer heat occurs, it may cause floding and consequential cleanup. The impact of this threat is: delays and associated costs. | B | Mitigate | Enhance drainage
A002 | Quality / Scope | Skills: If a shortage of skilled workers caused by industry demand occurs, it may cause an increase in test failures. The impact of this threat is: delays, rework and increased costs. | Skills | shortage of skilled workers | industry demand | an increase in test failures | threat | delays, rework and increased costs | H | H | 0.75 | 0.75 | 1.5 | A | Transfer | Contract development to a capable organisation | A002 | Quality / Scope | Skills: If a shortage of skilled workers caused by industry demand occurs, it may cause an increase in test failures. The impact of this threat is: delays, rework and increased costs. | A | Transfer | Contract development to a capable organisation | Quality / Scope | VL | opportunity
A003 | Cost / Value | Exchange Rates: If a improvement in the exchange rates caused by the value of the AU$ occurs, it may cause off-shored work will become cheaper. The impact of this opportunity is: improving profitability. | Exchange Rates | improvement in the exchange rates | the value of the AU$ | off-shored work will become cheaper | opportunity | improving profitability | M | L | 0.5 | 0.3 | 0.8 | D | Enhance | Monitor the exchange rate and include in decisions on contracts | A003 | Cost / Value | Exchange Rates: If a improvement in the exchange rates caused by the value of the AU$ occurs, it may cause off-shored work will become cheaper. The impact of this opportunity is: improving profitability. | D | Enhance | Monitor the exchange rate and include in decisions on contracts | Time | L | threat
A004 | [12 empty] | 0 | [9 empty] | Cost / Value | M | Avoid
A005 | [12 empty] | 0 | [9 empty] | Safety | H | Transfer
A006 | [12 empty] | 0 | [9 empty] | Reputation | VH | Mitigate
A007 |  |  |  | Locked in Sample Version | [8 empty] | 0 | [9 empty] | - |  | Active Acceptance
A008 | [12 empty] | 0 | [9 empty] | - |  | Passive Acceptance
A009 | [12 empty] | 0 | [9 empty] | - |  | Enhance
A010 | [12 empty] | 0 | [9 empty] | - |  | Share
A011 | [12 empty] | 0 | [9 empty] | - |  | Exploit
A012 | [12 empty] | 0
A013 | [12 empty] | 0
A014 | [12 empty] | 0
A015 | [12 empty] | 0
A016 | [12 empty] | 0
A017 | [12 empty] | 0
A018 | [12 empty] | 0
A019 | [12 empty] | 0
A020 | [12 empty] | 0
A021 | [12 empty] | 0
A022 | [12 empty] | 0
A023 | [12 empty] | 0
A024 | [12 empty] | 0
A025 | [12 empty] | 0
A026 | [12 empty] | 0
A027 | [12 empty] | 0
A028 | [12 empty] | 0
A029 | [12 empty] | 0
A030 | [12 empty] | 0
A031 | [12 empty] | 0
A032 | [12 empty] | 0
A033 | [12 empty] | 0
A034 | [12 empty] | 0
A035 | [12 empty] | 0
A036 | [12 empty] | 0
A037 | [12 empty] | 0
A038 | [12 empty] | 0
A039 | [12 empty] | 0
A040 | [12 empty] | 0
A041 | [12 empty] | 0
A042 | [12 empty] | 0
A043 | [12 empty] | 0
A044 | [12 empty] | 0
A045 | [12 empty] | 0
A046 | [12 empty] | 0
A047 | [12 empty] | 0
A048 | [12 empty] | 0
A049 | [12 empty] | 0
A050 | [12 empty] | 0
A051 | [12 empty] | 0
A052 | [12 empty] | 0
A053 | [12 empty] | 0
A054 | [12 empty] | 0
A055 | [12 empty] | 0
A056 | [12 empty] | 0
A057 | [12 empty] | 0
A058 | [12 empty] | 0
A059 | [12 empty] | 0
A060 | [12 empty] | 0
A061 | [12 empty] | 0
A062 | [12 empty] | 0
A063 | [12 empty] | 0
A064 | [12 empty] | 0
A065 | [12 empty] | 0
A066 | [12 empty] | 0
A067 | [12 empty] | 0
A068 | [12 empty] | 0
A069 | [12 empty] | 0
A070 | [12 empty] | 0
A071 | [12 empty] | 0
A072 | [12 empty] | 0
A073 | [12 empty] | 0
A074 | [12 empty] | 0
A075 | [12 empty] | 0
A076 | [12 empty] | 0
A077 | [12 empty] | 0
A078 | [12 empty] | 0
A079 | [12 empty] | 0
A080 | [12 empty] | 0
A081 | [12 empty] | 0
A082 | [12 empty] | 0
A083 | [12 empty] | 0
A084 | [12 empty] | 0
A085 | [12 empty] | 0
A086 | [12 empty] | 0
A087 | [12 empty] | 0
A088 | [12 empty] | 0
A089 | [12 empty] | 0
A090 | [12 empty] | 0
A091 | [12 empty] | 0
A092 | [12 empty] | 0
A093 | [12 empty] | 0
A094 | [12 empty] | 0
A095 | [12 empty] | 0
A096 | [12 empty] | 0
A097 | [12 empty] | 0
A098 | [12 empty] | 0
A099 | [12 empty] | 0
A100 | [12 empty] | 0
A101 | [12 empty] | 0
A102 | [12 empty] | 0
A103 | [12 empty] | 0
A104 | [12 empty] | 0
A105 | [12 empty] | 0
A106 | [12 empty] | 0
A107 | [12 empty] | 0
A108 | [12 empty] | 0
A109 | [12 empty] | 0
A110 | [12 empty] | 0
A111 | [12 empty] | 0
A112 | [12 empty] | 0
A113 | [12 empty] | 0
A114 | [12 empty] | 0
A115 | [12 empty] | 0
A116 | [12 empty] | 0
A117 | [12 empty] | 0
A118 | [12 empty] | 0
A119 | [12 empty] | 0
A120 | [12 empty] | 0
A121 | [12 empty] | 0
A122 | [12 empty] | 0
A123 | [12 empty] | 0
A124 | [12 empty] | 0
A125 | [12 empty] | 0
A126 | [12 empty] | 0
A127 | [12 empty] | 0
A128 | [12 empty] | 0
A129 | [12 empty] | 0
A130 | [12 empty] | 0
A131 | [12 empty] | 0
A132 | [12 empty] | 0
A133 | [12 empty] | 0
A134 | [12 empty] | 0
A135 | [12 empty] | 0
A136 | [12 empty] | 0
A137 | [12 empty] | 0
A138 | [12 empty] | 0
A139 | [12 empty] | 0
A140 | [12 empty] | 0
A141 | [12 empty] | 0
A142 | [12 empty] | 0
A143 | [12 empty] | 0
A144 | [12 empty] | 0
A145 | [12 empty] | 0
A146 | [12 empty] | 0
A147 | [12 empty] | 0
A148 | [12 empty] | 0
A149 | [12 empty] | 0
A150 | [12 empty] | 0
A151 | [12 empty] | 0
A152 | [12 empty] | 0
A153 | [12 empty] | 0
A154 | [12 empty] | 0
A155 | [12 empty] | 0
A156 | [12 empty] | 0
A157 | [12 empty] | 0
A158 | [12 empty] | 0
A159 | [12 empty] | 0
A160 | [12 empty] | 0
A161 | [12 empty] | 0
A162 | [12 empty] | 0
A163 | [12 empty] | 0
A164 | [12 empty] | 0
A165 | [12 empty] | 0
A166 | [12 empty] | 0
A167 | [12 empty] | 0
A168 | [12 empty] | 0
A169 | [12 empty] | 0
A170 | [12 empty] | 0
A171 | [12 empty] | 0
A172 | [12 empty] | 0
A173 | [12 empty] | 0
A174 | [12 empty] | 0
A175 | [12 empty] | 0
A176 | [12 empty] | 0
A177 | [12 empty] | 0
A178 | [12 empty] | 0
A179 | [12 empty] | 0
A180 | [12 empty] | 0
A181 | [12 empty] | 0
A182 | [12 empty] | 0
A183 | [12 empty] | 0
A184 | [12 empty] | 0
A185 | [12 empty] | 0
A186 | [12 empty] | 0
A187 | [12 empty] | 0
A188 | [12 empty] | 0
A189 | [12 empty] | 0
A190 | [12 empty] | 0
A191 | [12 empty] | 0
A192 | [12 empty] | 0
A193 | [12 empty] | 0
A194 | [12 empty] | 0
A195 | [12 empty] | 0
A196 | [12 empty] | 0
A197 | [12 empty] | 0
A198 | [12 empty] | 0
A199 | [12 empty] | 0
A200 | [12 empty] | 0
0

## Instructions
Mosaic Project Services Pty Ltd
13 Martin Street
© Practical PMP Pty Ltd, 2010 | [10 empty] | South Melbourne, VIC 3205, Australia
Use of Spreadsheet | [10 empty] | www.mosaicprojects.com.au
Risk Classification | [10 empty] | Support: | help@mosaicprojects.com.au
Each risk is assigned a classification to assist in the assessment and management of the threats or opportunities. | [10 empty] | Sales: | www.mosaicprojects.com.au
These options are selected from drop down lists
Classification based on element of the project most affected:
|  | Quality / Scope |  | The risk will affect the quality of a deliverable or prevent the affect the achievement of a project objective
|  | Time |  | The risk will delay (or accelerate) the completion of a deliverable
|  | Cost / Value |  | The risk will cause a change in the cost or value of a deliverable or the project as a whole
|  | Safety |  | The risk will affect the wellbeing of people
|  | Reputation |  | The risk will affect the reputation of the organisation
Describing the Risk
The spreadsheet is designed to construct a standard statement for each risk using a structured 'risk meta language'.
Storms: If a heavy thunderstorm caused by summer heat occurs, it may cause flooding and consequential cleanup.
You enter the description in three parts
Short Name for the risk - this is used in conversation about the risk so needs to be succinct and unique.
Storms
Description of risk - the actual risk event described in a few words
heavy thunderstorm
Cause of risk - describe the cause if the risk and any identified 'triggers'. 'Triggers' are events that are likely to cause the risk to occur.
summer heat
Consequences of Risk - the affect on the project's objectives if the risk occurs.
flooding and consequential cleanup
The spreadsheet formats the elements into the standard risk statement above by adding the words highlighted in blue
Describing the Impact
The spreadsheet is also designed to describe the effect of the event using a structured 'risk meta language'.
The impact of this threat is: delays and associated costs.
You enter the description in two parts
Threat or Opportunity - select one.
|  |  | opportunity |  | Enhance the project
|  |  | threat |  | Damage the project
Consequences of the risk occurring (description of the effect)
Briefly describe the effect the risk will have if it occurs
delays and associated costs
Qualitative Risk assessment
Each risk is assessed on a scale from 'Very Low' to 'Very High' for both its probability and impact.
Probability Assessment
The project team need to assess the probability ratings, a guide is offered below - you need to make your own assessment
|  |  | Rating | Suggestion | [5 empty] | Team Assessment
|  |  | VL | Very Low - less than a 20%chance of the event occurring
|  |  | L | Low - the probability is between 20% and 50% that the event will occur
|  |  | M | Medium - the probability is between 50% and 70% that the event will occur
|  |  | H | High - the probability is between 70% and 90% that the event will occur
|  |  | VH | Very High - there is a better than 90% probability that the event will occur
Impact Assessment
The project team need to assess the value allocated to each rating for each risk category
|  |  | Rating | Suggestion | [5 empty] | Team Assessment
Quality / Scope
|  |  | VL | Minor defect that may not need rectification
|  |  | L | Minor defect that can be rectified later
|  |  | M | A defect that can easily be corrected during the work of the project
|  |  | H | A defect that may prevent the deliverable for achieving is specified function
|  |  | VH | A defect that will degrade the performance of the deliverable
Time
|  |  | VL | A delay of a one or two days that should be recoverable
|  |  | L | A delay of a several days that may be recoverable
|  |  | M | An excusable delay* to the completion of the project (or a milestone) | [6 empty] | *Excusable delays are compensated by an approved extension to the project completion date
|  |  | H | A non-compensatable delay that may cause the project to finish late
|  |  | VH | A non-compensatable delay that will cause a delay to the project completion
Cost / Value*
|  |  | VL | Less than 0.1% of the project's profits (or 0.01% of the value) | [6 empty] | * these values need to be converted to cash amounts
|  |  | L | Less than 1% of the project's profits (or 0.1% of the value)
|  |  | M | Less than 5% of the project's profits (or 0.5% of the value)
|  |  | H | Less than 10% of the project's profits (or 1% of the value)
|  |  | VH | More than 10% of the project's profits (or 1% of the value)
Safety
|  |  | VL | Minor injury or 'near miss' not requiring first aid
|  |  | L | Minor injury requiring on-site treatment (eg, a minor cut)
|  |  | M | Injury requiring first aid treatment
|  |  | H | Injury requiring off site medical treatment
|  |  | VH | Lost time injury (more than 1 day, or shift's work lost)
Reputation
|  |  | VL | Minimal change to the organisations reputation beyond those immediately affected
|  |  | L | Reputational changed within the immediate stakeholder community
|  |  | M | Short term reputational change reported in the media (good or bad)
|  |  | H | Significant reputational change with the potential to affect the share price
|  |  | VH | Significant reputational change with a measured affect on the share price
Probability and Impact Matrix
The combination of probability and impact produces the following matrix, graded from 'No action' to Extreme.
[5 empty] | VL | L | M | H | VH
|  |  |  | VH | C | B | B | A | Ex
|  |  |  | H | C | C | B | A | A
|  |  |  | M | D | D | C | B | B
|  |  |  | L | N | D | D | C | B
|  |  |  | VL | N | N | D | C | C
Organisational policy will determine what constitutes an acceptable risk profile for the project to proceed (or continue).
Suggested responses are:
|  |  | EX | Extreme risk - the project must be changed to remove all extreme risks before progressing
|  |  | A | Category A risks - the project should be changed to remove most 'A' risks, management may accept 1 or 2 if removal is not feasible.
|  |  | B | Category B risks - the project should be changed to remove the majority of B risks, a few may be acceptable
|  |  | C | Category C risks - the project should be changed to remove C risks where there is a distinct cost benefit
|  |  | D | Category D risks - the project should be changed to remove D risks where it is simple, otherwise place on a 'watch list'
|  |  | N | Category N risks - No action required, place on a 'watch list'
Risk Management
The final development in this spreadsheet is to make initial determinations on the risk response
Proposed Response
Select a response from the dropdown list
For Opportunities
|  | Enhance |  | Take action to increase the probability or impact of the event
|  | Share |  | Allow another party to benefit from the event (usually in exchange for a reciprocal benefit to you)
|  | Exploit |  | Change the project to exploit the opportunity
For Threats
|  | Avoid |  | Change the project to remove the threat
|  | Transfer |  | You pay to transfer the risk to another party (contracts or insurances)
|  | Mitigate |  | Take action to reduce the probability or impact of the event
For both Opportunities and Threats
|  | Active Acceptance |  |  | Accept the risk but prepare for it to occur (action plans, contingencies, etc)
|  | Passive Acceptance |  |  | Do nothing until the risk occurs (or its probability changes)
Suggested Actions/Options
If known suggest actions/options that may be used.
Transfer to Risk Management System
Once the risk response has been entered, the spreadsheet formats the data for transfer to the Risk Management spreadsheet - The 'Green' section
Copy one risk at a time into the Risk Management system. Work through the responses before copying the next risk across.
The number of lines needed for each response will vary.