## Master
|  |  | Project Name |  |  | Sample Rail Bridge (EVM Cost Data) |  |  |  |  | 0
|  |  | Duration Units |  |  | Months | Note: Minor differences between the data and date based calculations for PC are to be expected. See 'Instructions' Tab.
|  |  | Work Days Per Week |  |  | 6
|  |  | Project Start Date |  |  | 2021-11-15 |  | PC (Data) = | 10 | Months
Date Format used DD-MMM-YY
|  |  | Project End Date |  |  | 2022-09-15 |  | PC (Dates) = | 10.17 | Months
|  |  | Units of Measure |  |  | $ Australian
|  |  | Data Date |  |  | 2022-02-21 |  | Time Now = | 3.3 Months
Results:
| Planned Completion |  |  | 10 Months
| Time Now |  |  | 3 Months
| Time Earned |  |  | 3.2828 Months
| Work Performance Variance |  |  | 0.2828 Months |  | ( 7.3 Working Days )
| Work Performance Index |  |  | 1.0943
| Expected Completion |  |  | 9.1386 Months
| Variance At Completion |  |  | 0.8614 Months |  | ( 25.8 Calendar Days )
| Expected Completion Date |  |  | 2022-08-20 03:47
Note: This date is an approximation, WPM does not include a detailed calendar.
Graph Data
|  | Cumulative |  | Per Unit
| Time Units | WP | WA | WP | WA
| 1 | 705000 | 705000 | 705000 | 705000
| 2 | 1560000 | 1560000 | 855000 | 855000
| 3 | 3580000 | 4158000 | 2020000 | 2598000
| 4 | 5624000 | 4158000 | 2044000 | 0
| 5 | 7400000 | 4158000 | 1776000 | 0
| 6 | 9176000 | 4158000 | 1776000 | 0
| 7 | 10870000 | 4158000 | 1694000 | 0
| 8 | 12480000 | 4158000 | 1610000 | 0
| 9 | 13740000 | 4158000 | 1260000 | 0
| 10 | 15000000 | 4158000 | 1260000 | 0
| 11 | 15000000 | 4158000 | 0 | 0
| 12 | 15000000 | 4158000 | 0 | 0
| 13 | 15000000 | 4158000 | 0 | 0
| 14 | 15000000 | 4158000 | 0 | 0
| 15 | 15000000 | 4158000 | 0 | 0
| 16 | 15000000 | 4158000 | 0 | 0
| 17 | 15000000 | 4158000 | 0 | 0
| 18 | 15000000 | 4158000 | 0 | 0
| 19 | 15000000 | 4158000 | 0 | 0
| 20 | 15000000 | 4158000 | 0 | 0
| 21 | 15000000 | 4158000 | 0 | 0
| 22 | 15000000 | 4158000 | 0 | 0
| 23 | 15000000 | 4158000 | 0 | 0
| 24 | 15000000 | 4158000 | 0 | 0
| 25 | 15000000 | 4158000 | 0 | 0
| 26 | 15000000 | 4158000 | 0 | 0
| 27 | 15000000 | 4158000 | 0 | 0
| 28 | 15000000 | 4158000 | 0 | 0
| 29 | 15000000 | 4158000 | 0 | 0
| 30 | 15000000 | 4158000 | 0 | 0
| 31 | 15000000 | 4158000 | 0 | 0
| 32 | 15000000 | 4158000 | 0 | 0
| 33 | 15000000 | 4158000 | 0 | 0
| 34 | 15000000 | 4158000 | 0 | 0
| 35 | 15000000 | 4158000 | 0 | 0
| 36 | 15000000 | 4158000 | 0 | 0
| 37 | 15000000 | 4158000 | 0 | 0
| 38 | 15000000 | 4158000 | 0 | 0
| 39 | 15000000 | 4158000 | 0 | 0
| 40 | 15000000 | 4158000 | 0 | 0
| 41 | 15000000 | 4158000 | 0 | 0
| 42 | 15000000 | 4158000 | 0 | 0
| 43 | 15000000 | 4158000 | 0 | 0
| 44 | 15000000 | 4158000 | 0 | 0
| 45 | 15000000 | 4158000 | 0 | 0
| 46 | 15000000 | 4158000 | 0 | 0
| 47 | 15000000 | 4158000 | 0 | 0
| 48 | 15000000 | 4158000 | 0 | 0
| 49 | 15000000 | 4158000 | 0 | 0
| 50 | 15000000 | 4158000 | 0 | 0
| 51 | 15000000 | 4158000 | 0 | 0
| 52 | 15000000 | 4158000 | 0 | 0
| 53 | 15000000 | 4158000 | 0 | 0
| 54 | 15000000 | 4158000 | 0 | 0
| 55 | 15000000 | 4158000 | 0 | 0
| 56 | 15000000 | 4158000 | 0 | 0
| 57 | 15000000 | 4158000 | 0 | 0
| 58 | 15000000 | 4158000 | 0 | 0
| 59 | 15000000 | 4158000 | 0 | 0
| 60 | 15000000 | 4158000 | 0 | 0
| Check Sums | 830135000 | 243429000 | 15000000 | 4158000
Sample Rail Bridge (EVM Cost Data)

## WA
Work Accomplished: Sample Rail Bridge (EVM Cost Data)
|  |  | Data Date = |  | 2022-02-21 |  |  | Work Periods to TN = |  |  | 3.3 Months
Use this page to record the work accomplished during each Months
Between 1 and 14 line items can be entered to record the work. Descriptions of the work can be included in the first column.
The work completed on variations may be recorded in the 'Variation' section below or simply included in the oveall work accomplished.
The work units for this project are: $ Australian
[6 empty] | Data Date from Master = |  |  | 3.3 Months
[6 empty] | Time Now (TN) from below = |  |  | 3 | Time Earned (TE) = |  | 3.2828
Months No. | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Include in TN Count | bar: 1 to 60
$ Australian Cumulative | [5 empty] | 1: 705000; 2: 1560000; 3: 4158000
Total $ Australian per Months | [5 empty] | 705000 | 855000 | 2598000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baseline Work Accomplished: |  |  |  | Total Recorded
Project management and overheads | Project management and overheads | Project management and overheads | Project management and overheads | 255000 |  | 1: 85000; 2: 85000; 3: 85000
Site management and services | Site management and services | Site management and services | Site management and services | 90000 |  | 3: 90000
Design & Approvals | Design & Approvals | Design & Approvals | Design & Approvals | 1550000 |  | 1: 620000; 2: 620000; 3: 310000
Site set up | Site set up | Site set up | Site set up | 300000 |  | 2: 150000; 3: 150000
Earth works | Earth works | Earth works | Earth works | 1125000 |  | 3: 1125000
Manfr. & Install PC Bridge Deck | Manfr. & Install PC Bridge Deck | Manfr. & Install PC Bridge Deck | Manfr. & Install PC Bridge Deck | 780000 |  | 3: 780000
Concrete piers & walls | Concrete piers & walls | Concrete piers & walls | Concrete piers & walls | 58000 |  | 3: 58000
Embankment works | Embankment works | Embankment works | Embankment works | 0
Track works | Track works | Track works | Track works | 0
Clear Site & Make Good | Clear Site & Make Good | Clear Site & Make Good | Clear Site & Make Good | 0
0
0
0
0
Variation Work Accomplished:
Variation total per Months | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Calculation TE
|  |  | Work Planned Cumulative |  |  | 1: 705000; 2: 1560000; 3: 3580000; 4: 5624000; 5: 7400000; 6: 9176000; 7: 10870000; 8: 12480000; 9: 13740000; 10: 15000000
|  |  | Work Accomplished Cumulative |  |  | 1: 705000; 2: 1560000; 3: 4158000
|  |  | Interger |  |  | 1: 0; 2: 2; 3: 3
|  |  | Offset |  |  | 1: 0; 2: 0; 3: 0
|  |  | Numerator |  |  | 1: 705000; 2: 0; 3: 578000
|  |  | Denominator |  |  | 1: 705000; 2: 2020000; 3: 2044000
|  |  | Fraction |  |  | 1: 1; 2: 0; 3: 0.28278
|  |  | Time Earned (TE) |  |  | 1: 1; 2: 2; 3: 3.2828

## WP
|  |  | Work Planned: |  |  |  | Sample Rail Bridge (EVM Cost Data)
Establish your Baseline for Worked Planned at the start of the project (this should not change). The values entered are per Months
Between 1 and 14 line items can be entered to establish the plan. Descriptions of the work can be included in the first column.
Variations to the planned baseline can be added in the 'Variation' section below.
The work units for this project are: $ Australian
|  |  |  | The planned duration for this project (Dates) is: |  |  |  |  | 10.17
|  |  |  | WP Planned Completion (PC) = |  |  |  | 10
Months No. |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Include in PC Count | bar: 1 to 60
$ Australian Cumulative |  |  |  |  | 1: 705000; 2: 1560000; 3: 3580000; 4: 5624000; 5: 7400000; 6: 9176000; 7: 10870000; 8: 12480000; 9: 13740000; 10: 15000000
Total $ Australian per Months |  |  |  |  | 705000 | 855000 | 2020000 | 2044000 | 1776000 | 1776000 | 1694000 | 1610000 | 1260000 | 1260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baseline Work Planned: |  |  |  | Total Allocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project management and overheads | Project management and overheads | Project management and overheads | Project management and overheads | 850000 | 1: 85000; 2: 85000; 3: 85000; 4: 85000; 5: 85000; 6: 85000; 7: 85000; 8: 85000; 9: 85000; 10: 85000
Site management and services | Site management and services | Site management and services | Site management and services | 600000 | 3: 75000; 4: 75000; 5: 75000; 6: 75000; 7: 75000; 8: 75000; 9: 75000; 10: 75000
Design & Approvals | Design & Approvals | Design & Approvals | Design & Approvals | 1550000 | 1: 620000; 2: 620000; 3: 310000
Site set up | Site set up | Site set up | Site set up | 300000 | 2: 150000; 3: 150000
Earth works | Earth works | Earth works | Earth works | 1500000 | 3: 750000; 4: 750000
Manfr. & Install PC Bridge Deck | Manfr. & Install PC Bridge Deck | Manfr. & Install PC Bridge Deck | Manfr. & Install PC Bridge Deck | 3900000 | 3: 650000; 4: 650000; 5: 650000; 6: 650000; 7: 650000; 8: 650000
Concrete piers & walls | Concrete piers & walls | Concrete piers & walls | Concrete piers & walls | 2900000 | 4: 484000; 5: 966000; 6: 966000; 7: 484000
Embankment works | Embankment works | Embankment works | Embankment works | 1200000 | 7: 400000; 8: 800000
Track works | Track works | Track works | Track works | 1700000 | 9: 1100000; 10: 600000
Clear Site & Make Good | Clear Site & Make Good | Clear Site & Make Good | Clear Site & Make Good | 500000 | 10: 500000
0
0
0
0
Variation Work Planned:
Variation total per Months |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Instructions
Work Performance Management - Spreadsheet
This Excel Workbook and the WPM Logo are © copyright Mosaic Project Services Pty Ltd and ™ trademarked.
Mosaic Project Services Pty Ltd PO Box 5150, South Melbourne VIC 3125, Australia.
The WPM methodology is available for use and adaptation under a Creative Commons 3.0 License, download from:
https://mosaicprojects.com.au/shop-easy-WPM_WS.php
General Use
The spreadsheets and workbook are protected to ensure the calculations perform as intended. Data Entry is allowed in the fields with a White fill. The project set up information at the top of the Master sheet is required for the calculations. All fields are needed, when complete the red WARNING is no longer shown. Provided the required data has been entered correctly, all calculations are performed automatically. For more information see the PFD file 'WPM Instructions for Use' downloaded with this spreadsheet. Copies of this document can be obtained from:
https://mosaicprojects.com.au/shop-easy-WPM_WS.php
Project Set Up
Project Name - Enter an appropriate project name, this is used across the spreadsheets.
Duration Units - the spreadsheet is set up to calculate 60 Months (5 years), 60 weeks or 60 days. Select your preferred time unit for each work period from the pull-down list.
Work Days Per Week - Select the number of working days per week from the pull-down list.
Project Start and End Dates. Start and end dates are required for the calculations. Date format in this version of the spreadsheet is DD/Month/YY.
Units of Measure - describes the way work is measured. This can be any unit of your choosing from $ Dollars, through 'Story Points', to the work outputs being counted.
Work Planned (WP)
The Work Planned is the foundation of the WPM calculations, enter the number of units of work planned to be produced in each work period. The values entered are per the 'Units of Measure' established during the project set up. Where the project is still working, but no production is planned in a time period, enter Zero (0) in at least one cell. This ensures the time period is included in the PC count. The baseline for Worked Planned is set at the start of the project (this should not change). Between 1 and 14 line-items can be entered to establish the plan - at least one set of data is needed. Descriptions of the work can be included in the first column. Variations to the planned baseline can be added in the 'Variation' section in the lower part of the screen.
Work Accomplished (WA)
The Work Accomplished is recorded at the end of each work period. The values entered are as per the 'Units of Measure' used to establish the Work Planned. Between 1 and 14 line items can be entered to establish the plan - at least one set of data is needed. The Work Accomplished should be recorded against the same line items as used in the WP. Where needed, descriptions of the work can be included in the first column. Work Accomplished on Variations may be entered in the 'Variation' section in the lower part of the screen.
Results & Calculations
The Calculations are automatic and occur as data is entered. Complete all input as at a date before using the results. A difference between the PC (Data) and PC (Calendar) durations is expected and has two sources. Minor differences are due to the data always working in whole units, the start and finish dates may not be precisely at the start, or end, of a week, or month, this is not a problem. The second cause is the number of time periods in the WP data set are different to the number between the dates, this error needs correcting. Any variance is adjusted against the project completion date. The Report tab holds a formatted report to output the information assessed as at Time Now.
Duration Units
Select Unit
Months
Weeks
Days
Work Days Per Week
Select Number
4
5
6
7

## Report
Sample Rail Bridge (EVM Cost Data)
| Time Now = | 2022-02-21
Planned Completion |  | 10 Months
Time Now |  | 3 Months
Time Earned |  | 3.2828 Months
Work Performance Variance |  | 0.2828 Months | ( 7.3 Working Days )
Work Performance Index |  | 1.0943
Expected Completion |  | 9.1386 Months
Variance At Completion |  | 0.8614 Months | ( 25.8 Calendar Days )
Expected Completion Date |  | 2022-08-20 03:47
Note: This date is an approximation, WPM does not include a detailed calendar.